## Project Plan and Gantt
ROADMAP
Name | NPTEL LOCAL CHAPTER
SPOC | DR. DIPAK KUMAR KOLE
Start Date | August 10, 2017
End Date | April 30, 2017
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | SPOC, Coordinator | 2017-11-23 | 2017-11-23 | 0 | C
Agree on objectives | SPOC, Coordinator | 2017-12-15 | 2017-12-15 | 0 | C
Prepare presentation | Swarna, Sraboni | 2017-12-15 | 2018-01-03 | 19 | P
Start Campaigning | Entire Committee | 2018-01-05 | 2018-01-11 | 6 | N
Cash Collection | Aniket, Swarna | 2018-01-05 | 2018-01-22 | 17 | N
Google form mgmt. | Anik, Subhrasankar | 2018-01-07 | 2018-01-17 | 10 | N
Social Media Marketing | Anurag, Protyay | 2017-12-26 | 2018-01-20 | 25 | N
Collaboration(SIT) | Anik, Haranath | 2018-01-03 | 2018-01-03 | 0 | N
End Date | NA | NA | 2018-04-30 | NA
Legends
C | Complete
N | Not started
P | In Progress
PIE CHART REPRESENTATION OF ACTIVITIES | PIE CHART REPRESENTATION OF ACTIVITIES