## Project Plan and Gantt
ROADMAP
Name | NPTEL LOCAL CHAPTER
SPOC | DR. DIPAK KUMAR KOLE
Start Date | August 10, 2017
End Date | April 30, 2017
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | PIE CHART REPRESENTATION OF ACTIVITIES
Set kick-off meeting | SPOC, Coordinator | 2017-11-23 | 2017-11-23 | 0 | Complete
Agree on objectives | SPOC, Coordinator | 2017-12-15 | 2017-12-15 | 0 | Complete
Prepare presentation | Swarna, Sraboni | 2017-12-15 | 2018-01-03 | 19 | In progress
Start Campaigning | Entire Committee | 2018-01-05 | 2018-01-11 | 6 | Not started
Cash Collection | Aniket, Swarna | 2018-01-05 | 2018-01-22 | 17 | Not started
Google form mgmt. | Anik, Subhrasankar | 2018-01-07 | 2018-01-17 | 10 | Not started
Social Media Marketing | Anurag, Haranath, Protyay | 2017-12-26 | 2018-01-20 | 25 | Not started
Collaboration(SIT) | Anik, Haranath(tentative) | 2018-01-03 | 2018-01-03 | 0 | Not started
End Date | NA | NA | 2018-04-30 | NA